## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conceptions |  | 18 | 18 | 0 |  |  |  |  | 100%
1.1 | Project functionalities | SS | 11 | 11 | 0 | 1 | 2023-07-10 | 2023-07-12 | 3 | 100% | bar: WEEK 1 M to WEEK 1 W; WEEK 8 W
1.2 | Research | RG | 3 | 3 | 0 | 1 | 2023-07-12 | 2023-07-13 | 2 | 100% | bar: WEEK 1 W to WEEK 1 R; WEEK 8 W
1.3 | Projections | PM | 3 | 3 | 0 | 1 | 2023-07-13 | 2023-07-14 | 2 | 100% | bar: WEEK 1 R to WEEK 1 F; WEEK 8 W
1.4 | Stakeholders | CM | 1 | 1 | 0 | 1 | 2023-07-14 | 2023-07-14 | 1 | 100% | bar: WEEK 1 F; WEEK 8 W
2 | Project Documentations |  | 40 | 40 | 0 |  |  |  |  | 100%
2.1 | User Stories | RG | 12 | 12 | 0 | 1 | 2023-07-17 | 2023-07-18 | 2 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 8 W
2.2 | Balsamiq | CM | 13 | 13 | 0 | 1 | 2023-07-18 | 2023-07-21 | 4 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 8 W
2.3 | Function Points | PM | 8 | 8 | 0 | 1 | 2023-07-24 | 2023-07-26 | 3 | 100% | bar: WEEK 3 M to WEEK 3 W; WEEK 8 W
2.4 | COCOMOII | PM | 7 | 7 | 0 | 1 | 2023-07-26 | 2023-07-27 | 2 | 100% | bar: WEEK 3 W to WEEK 3 R; WEEK 8 W
3 | System Configuration |  | 56 | 56 | 0 |  |  |  |  | 100%
3,1 | Maven Configuration | SS | 6 | 6 | 0 | 2 | 2023-07-31 | 2023-08-02 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W; WEEK 8 W
3,2 | Docker Configuration | RG | 7 | 7 | 0 | 2 | 2023-07-31 | 2023-08-02 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W; WEEK 8 W
3,3 | PostegreSQL Configuration | SS | 6 | 6 | 0 | 2 | 2023-08-03 | 2023-08-04 | 2 | 100% | bar: WEEK 4 R to WEEK 4 F; WEEK 8 W
3,4 | RabbitMQ Configuration | RG | 8 | 8 | 0 | 2 | 2023-08-03 | 2023-08-04 | 2 | 100% | bar: WEEK 4 R to WEEK 4 F; WEEK 8 W
3,5 | Web Interface Configuration | CM | 8 | 8 | 0 | 2 | 2023-08-08 | 2023-08-10 | 3 | 100% | bar: WEEK 5 T to WEEK 5 R; WEEK 8 W
3,6 | Broadcast Configuration | PM | 9 | 9 | 0 | 2 | 2023-08-09 | 2023-08-11 | 3 | 100% | bar: WEEK 5 W to WEEK 5 F; WEEK 8 W
3,7 | Multiple Docker-Compose organization | SS | 4 | 4 | 0 | 2 | 2023-08-14 | 2023-08-14 | 1 | 100% | bar: WEEK 6 M; WEEK 8 W
3,8 | REST API Configuration | RG | 8 | 8 | 0 | 2 | 2023-08-16 | 2023-08-18 | 3 | 100% | bar: WEEK 6 W to WEEK 6 F; WEEK 8 W
4 | Referendum Implementation Backend |  | 63 | 63 | 0 |  |  |  |  | 100%
4,1 | Referendum proposal functionality | CM | 5 | 5 | 0 | 3 | 2023-08-21 | 2023-08-22 | 2 | 100% | bar: WEEK 7 M to WEEK 7 T; WEEK 8 W
4,2 | Referendum answer functionality | PM | 5 | 5 | 0 | 3 | 2023-08-23 | 2023-08-24 | 2 | 100% | bar: WEEK 7 W to WEEK 7 R; WEEK 8 W
4,3 | Referendum display functionality | SS | 5 | 5 | 0 | 3 | 2023-08-24 | 2023-08-25 | 2 | 100% | bar: WEEK 7 R to WEEK 7 F; WEEK 8 W
4,4 | Supporting number view functionality | CM | 5 | 5 | 0 | 3 | 2023-08-28 | 2023-08-30 | 3 | 100% | bar: WEEK 8 M to WEEK 8 W
4,5 | Referendum database organization | RG | 6 | 6 | 0 | 3 | 2023-08-29 | 2023-08-31 | 3 | 100% | bar: WEEK 8 T to WEEK 8 R
4,6 | Consensus Referendum database organization | SS | 5 | 5 | 0 | 3 | 2023-08-30 | 2023-09-01 | 3 | 100% | bar: WEEK 8 W to WEEK 8 F
4,7 | Referendum first Consensus | RG | 14 | 14 | 0 | 3 | 2023-09-04 | 2023-09-08 | 5 | 100% | bar: WEEK 8 W; WEEK 9 M to WEEK 9 F
4,8 | Referendum second Consensus | SS | 14 | 14 | 0 | 3 | 2023-09-04 | 2023-09-08 | 5 | 100% | bar: WEEK 8 W; WEEK 9 M to WEEK 9 F
4,9 | Citizens voting system | PM | 4 | 4 | 0 | 3 | 2023-09-07 | 2023-09-08 | 2 | 100% | bar: WEEK 8 W; WEEK 9 R to WEEK 9 F
5 | Setting Implementation |  | 16 | 16 | 0 |  |  |  |  | 100%
5,1 | Nation selection functionality | PM | 4 | 4 | 0 | 4 | 2023-09-11 | 2023-09-12 | 2 | 100% | bar: WEEK 8 W; WEEK 10 M to WEEK 10 T
5,2 | Citizen registration functionality | CM | 5 | 5 | 0 | 4 | 2023-09-12 | 2023-09-13 | 2 | 100% | bar: WEEK 8 W; WEEK 10 T to WEEK 10 W
5,3 | Citizen authentication functionality | SS | 3 | 3 | 0 | 4 | 2023-09-13 | 2023-09-13 | 1 | 100% | bar: WEEK 8 W; WEEK 10 W
5,4 | Nation representative auth functionality | RG | 4 | 4 | 0 | 4 | 2023-09-14 | 2023-09-14 | 1 | 100% | bar: WEEK 8 W; WEEK 10 R
6 | Referendum Implementation Frontend |  | 41 | 41 | 0 |  |  |  |  | 100%
6,1 | Referendum display | CM | 5 | 5 | 0 | 4 | 2023-09-18 | 2023-09-20 | 3 | 100% | bar: WEEK 8 W; WEEK 11 M to WEEK 11 W
6,2 | Citizens voting interface | PM | 6 | 6 | 0 | 4 | 2023-09-18 | 2023-09-20 | 3 | 100% | bar: WEEK 8 W; WEEK 11 M to WEEK 11 W
6,3 | Citizen Registration interface | CM | 5 | 5 | 0 | 4 | 2023-09-21 | 2023-09-22 | 2 | 100% | bar: WEEK 8 W; WEEK 11 R to WEEK 11 F
6,4 | Citizen Authentication interface | PM | 6 | 6 | 0 | 4 | 2023-09-21 | 2023-09-22 | 2 | 100% | bar: WEEK 8 W; WEEK 11 R to WEEK 11 F
6,5 | Nation representative Authentication interface | RG | 5 | 5 | 0 | 4 | 2023-09-25 | 2023-09-26 | 2 | 100% | bar: WEEK 8 W; WEEK 12 M to WEEK 12 T
6,6 | Referendum proposal interface | SS | 4 | 4 | 0 | 4 | 2023-09-26 | 2023-09-27 | 2 | 100% | bar: WEEK 8 W; WEEK 12 T to WEEK 12 W
6,7 | Referendum answer interface | RG | 5 | 5 | 0 | 4 | 2023-09-26 | 2023-09-27 | 2 | 100% | bar: WEEK 8 W; WEEK 12 T to WEEK 12 W
6,8 | Referendum results interface | SS | 5 | 5 | 0 | 4 | 2023-09-28 | 2023-09-29 | 2 | 100% | bar: WEEK 8 W; WEEK 12 R to WEEK 12 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 234 | 234 | 0 | 60 | 3.9 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 234 | 230.1 | 226.2 | 222.3 | 218.4 | 214.5 | 210.6 | 206.7 | 202.8 | 198.9 | 195 | 191.1 | 187.2 | 183.3 | 179.4 | 175.5 | 171.6 | 167.7 | 163.8 | 159.9 | 156 | 152.1 | 148.2 | 144.3 | 140.4 | 136.5 | 132.6 | 128.7 | 124.8 | 120.9 | 117 | 113.1 | 109.2 | 105.3 | 101.4 | 97.5 | 93.6 | 89.7 | 85.8 | 81.9 | 78 | 74.1 | 70.2 | 66.3 | 62.4 | 58.5 | 54.6 | 50.7 | 46.8 | 42.9 | 39 | 35.1 | 31.2 | 27.3 | 23.4 | 19.5 | 15.6 | 11.7 | 7.8 | 3.9
[10 empty] | ESTIMATE | 234 | 229 | 224 | 221 | 218 | 216 | 210 | 203 | 199 | 194 | 191 | 187 | 184 | 180 | 176 | 176 | 172 | 168 | 163 | 156 | 149 | 149 | 146 | 141 | 135 | 132 | 128 | 128 | 125 | 122 | 120 | 118 | 115 | 112 | 108 | 105 | 103 | 98 | 93 | 90 | 89 | 82 | 75 | 70 | 65 | 57 | 54 | 49 | 45 | 41 | 41 | 37 | 33 | 30 | 25 | 19 | 16 | 11 | 5 | 1 | 7163
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 5 | 5 | 3 | 3 | 2 | 6 | 7 | 4 | 5 | 3 | 4 | 3 | 4 | 4 | 0 | 4 | 4 | 5 | 7 | 7 | 0 | 3 | 5 | 6 | 3 | 4 | 0 | 3 | 3 | 2 | 2 | 3 | 3 | 4 | 3 | 2 | 5 | 5 | 3 | 1 | 7 | 7 | 5 | 5 | 8 | 3 | 5 | 4 | 4 | 0 | 4 | 4 | 3 | 5 | 6 | 3 | 5 | 6 | 4 | 1 | 234
[10 empty] | HRS REMAINING | 229 | 224 | 221 | 218 | 216 | 210 | 203 | 199 | 194 | 191 | 187 | 184 | 180 | 176 | 176 | 172 | 168 | 163 | 156 | 149 | 149 | 146 | 141 | 135 | 132 | 128 | 128 | 125 | 122 | 120 | 118 | 115 | 112 | 108 | 105 | 103 | 98 | 93 | 90 | 89 | 82 | 75 | 70 | 65 | 57 | 54 | 49 | 45 | 41 | 41 | 37 | 33 | 30 | 25 | 19 | 16 | 11 | 5 | 1 | 0 | 6929

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Project Conceptions | Project functionalities | Building the idea of the project | SS | 11 | Completed |  | Not Started | 1
Medium | 1 | Project Conceptions | Research | Doing research of the tools | RG | 3 | Completed |  | In Progress | 3
Low | 1 | Project Conceptions | Projections | Define the projections and the workflow | PM | 3 | Completed |  | Completed | 4
Low | 1 | Project Conceptions | Stakeholders | Define the stakeholders of the project | CM | 1 | Completed |  |  | 5
High | 1 | Project Documentations | User Stories | Define the user stories of the system | RG | 12 | Completed |  |  | 6
High | 1 | Project Documentations | Balsamiq | Build the project from scratch | CM | 13 | Completed |  |  | 7
High | 1 | Project Documentations | Function Points | Fix the function points | PM | 8 | Completed |  |  | 8
High | 1 | Project Documentations | COCOMOII | Use of COCOMO Method | PM | 7 | Completed |  |  | 9
Medium | 2 | System Configuration | Maven Configuration | Setup the Maven deployments | SS | 6 | Completed |  |  | 11
High | 2 | System Configuration | Docker Configuration | Setup the JAVA User API server as a docker image | RG | 7 | Completed |  |  | 12
High | 2 | System Configuration | PostegreSQL Configuration | Setup and configure the PostegreSQL as a Docker image | SS | 6 | Completed |  |  | 13
High | 2 | System Configuration | RabbitMQ Configuration | Setup and configure the RabbitMQ server as a Docker image | RG | 8 | Completed |  |  | 14
High | 2 | System Configuration | Web Interface Configuration | Create the Web Interface Configurationand create basic preliminary GUI | CM | 8 | Completed |  |  | 15
High | 2 | System Configuration | Broadcast Configuration | Configurate the Broadcast Service to allow the exchange of messages between different Nations | PM | 9 | Completed |  |  | 16
Medium | 2 | System Configuration | Multiple Docker-Compose organization | Setup and organise the different Docker-Compose | SS | 4 | Completed
High | 2 | System Configuration | REST API Configuration | Setup the REST API Configuration | RG | 8 | Completed
Medium | 3 | Referendum Implementation Backend | Referendum proposal functionality | Create functionality to propose referendum | CM | 5 | Completed
Medium | 3 | Referendum Implementation Backend | Referendum answer functionality | Create functionality to answer referendum | PM | 5 | Completed
Medium | 3 | Referendum Implementation Backend | Referendum display functionality | Create functionality to display referendum on page | SS | 5 | Completed
Medium | 3 | Referendum Implementation Backend | Supporting number view functionality | Create functionality to display info about the referendum (number of votes) | CM | 5 | Completed
High | 3 | Referendum Implementation Backend | Referendum database organization | Organise the object Referendum in the database | RG | 6 | Completed
High | 3 | Referendum Implementation Backend | Consensus Referendum database organization | Organise the object Consensus Referendum in the database | SS | 5 | Completed
High | 3 | Referendum Implementation Backend | Referendum first Consensus | Build the Consensus primitive to decide if the nations want to do the Referendum | RG | 14 | Completed
High | 3 | Referendum Implementation Backend | Referendum second Consensus | Build the Consensus primitive to decide if the citizens agree with the Referendum | SS | 14 | Completed
Medium | 3 | Referendum Implementation Backend | Citizens voting system | Build the primitive to allow the citizens to vote | PM | 4 | Completed
Low | 4 | Setting Implementation | Nation selection functionality | Create functionality to allow selection of the Nation | PM | 4 | Completed
Low | 4 | Setting Implementation | Citizen registration functionality | Create functionality to allow registration of the user | CM | 5 | Completed
Low | 4 | Setting Implementation | Citizen authentication functionality | Create functionality to allow authentication and access of the user | SS | 3 | Completed
Low | 4 | Setting Implementation | Nation representative auth functionality | Create functionality to allow authentication and access of the nation | RG | 4 | Completed
Medium | 4 | Referendum Implementation Frontend | Referendum display | Build interface for the display of the Referendum | CM | 5 | Completed
Medium | 4 | Referendum Implementation Frontend | Citizens voting interface | Build interface for the voting of the citizens | PM | 6 | Completed
Low | 4 | Referendum Implementation Frontend | Citizen Registration interface | Build interface for the Citizen registration | CM | 5 | Completed
Low | 4 | Referendum Implementation Frontend | Citizen Authentication interface | Build interface for the Citizen authentication | PM | 6 | Completed
Low | 4 | Referendum Implementation Frontend | Nation representative Authentication interface | Build interface for the Nation representative authentication | RG | 5 | Completed
Medium | 4 | Referendum Implementation Frontend | Referendum proposal interface | Build interface for the proposal of the Referendum | SS | 4 | Completed
Medium | 4 | Referendum Implementation Frontend | Referendum answer interface | Build interface for the answer of the Referendum | RG | 5 | Completed
Medium | 4 | Referendum Implementation Frontend | Referendum results interface | Build interface for the results of the Referendum | SS | 5 | Completed

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
Role selection | As a user, I want to select the citizen or the national representative role, so that I can enter and navigate in the page hosted by that nation. | Chiara Maggi | 2023-07-17 | x
Citizen registration | As a citizen, I want to register myself in the page hosted by the nation related to my legal citizenship, so that I can authenticate myself in the future | Riccardo Gobbato | 2023-07-17 | x
Citizen authentication | As a citizen, I want to authenticate myself in the the page hosted by the nation related to my legal citizenship, so that I can access the national service | Chiara Maggi | 2023-07-17 | x
Nation representative authentication | As a nation representative, I want to authenticate myself in the context of my nation, so that I can manage the national service | Simone Scaccia | 2023-07-17 | x
Citizen personal area | As a citizen, I want to have a personal area displaying the possible services, so that I can choose a service (referendum, survey, information) | Riccardo Gobbato | 2023-07-17 | x
Supporting number at nation side | As a nation representative, I want to keep track of the number of supporting citizens in the context of a certain referendum idea, so that I can decide if declare or not the referendum, on the base of a certain threshold | Simone Scaccia | 2023-07-17 | x
Supporting number at citizen side | As a citizen, I want to see the number of supporting citizens in the context of a certain referendum idea, so that I can be informed about the evolution of the referendum idea support | Chiara Maggi | 2023-07-18 | x
Supported referendum acceptance notification | As a citizen, I want to receive a notification when a supported national referendum idea has reached the 1% threshold, so that I can know it has been accepted | Simone Scaccia | 2023-07-18 | x
National referendum declaration | As a nation rapresentative, I want to declare a new national referendum, constituted by one question with "Yes" or "No" answer, so that I can obtain votes from citizens of my nation | Pasquale Mocerino | 2023-07-18 | x
European referendum idea (consensus) | As a nation representative, I want to propose an idea for an European referendum to other European nations, so that it can be proposed to all European citizens | Riccardo Gobbato | 2023-07-18 | x
European referendum declaration | As a nation representative, I want to declare a new accepted European referendum, constituted by one question with "Yes" or "No" answer, so that I can obtain votes from citizens of my nation | Riccardo Gobbato | 2023-07-18 | x
Referendum display | As a citizen, I want to see the list of all referendums declared by my nation, distinguished between national ones and European ones, so that I can vote | Chiara Maggi | 2023-07-18 | x
Nation referendum notification | As a nation representative, I want to notify the citizens of my nation about a new declared referendum, so that I can inform them | Simone Scaccia | 2023-07-18 | x
Citizen referendum notification | As a citizen, I want to be notified by my nation about a new declared referendum, so that I can be up to date | Simone Scaccia | 2023-07-18 | x
Citizen referendum vote | As a citizen, I want to vote in a referendum declared by my nation, so that I can express my opinion | Pasquale Mocerino | 2023-07-18 | x
Referendum results at nation side | As a nation representative, I want to see the results of a declared referendum, so that I can take relative measures | Riccardo Gobbato | 2023-07-18 | x
Referendum results at citizen site | As a citizen, I want to see the results of a referendum declared by my nation, so that I can know the outcome | Chiara Maggi | 2023-07-18 | x
European referendum ideas display (consensus) | As a nation representative, I want to see all current European referendum ideas, so that I can know other nations opinions | Chiara Maggi | 2023-07-18 | x
European referendum idea support (consensus) | As a nation representative, I want to support or reject an idea of European referendum, so that the idea can be effectively proposed or not to European citizens | Simone Scaccia | 2023-07-18 | x
European referendum idea result (consensus) | As a nation representative, I want to see the final result of the supporting process related to an European referendum idea, so that I can know it has been accepted | Riccardo Gobbato | 2023-07-18 | x
European referendum result | As a nation representative, I want to see the final result of the voting process related to an European referendum, so that I can apply it if it has been approved by European citizens | Pasquale Mocerino | 2023-07-18 | x