## User Stories
EPIC | USER STORY | PRIORITY | VALUE | RISK | ESTIMATE | ACCEPTANCE | PRIORITY(INT) | VALUE(INT) | RISK(INT) | PRIORITY(INV) | VALUE(INV) | RISK(INV) | THEME(Sp) | FEATURE(Sp) | RELEASE(S) | ROW(S)
Nation selection | As a citizen, I want to select the nation related to my legal citizenship, so that I can navigate in the page hosted by that nation | 4 Low | 4 Low | 4 Low | LG | The user should see a button to change nation | 4 | 4 | 4 | 1 | 1 | 1 |  |  | #REF! | 2
Citizen registration | As a citizen, I want to register myself in the page hosted by the nation related to my legal citizenship, so that I can authenticate myself in the future | 3 Med | 3 Med | 3 Med | LG | The user should be able to do the registration in the site | 3 | 3 | 3 | 2 | 2 | 2 |  |  | #REF! | 3
Citizen authentication | As a citizen, I want to authenticate myself in the the page hosted by the nation related to my legal citizenship, so that I can access the national service | 3 Med | 3 Med | 3 Med | MD | The user should be able to do the authentication in the site | 3 | 3 | 3 | 2 | 2 | 2 |  |  | #REF! | 4
Nation representative authentication | As a nation representative, I want to authenticate myself in the context of my nation, so that I can manage the national service | 3 Med | 3 Med | 3 Med | MD | The nation representative should be able to do the authentication in the site | 3 | 3 | 3 | 2 | 2 | 2 |  |  | #REF! | 5
Citizen personal area | As a citizen, I want to have a personal area displaying the possible services, so that I can choose a service (referendum, survey, information) | 2 Med | 2 Med | 2 Med | MD | After logging in with correct credentials the user must be able to see the user panel. | 2 | 2 | 2 | 3 | 3 | 3 |  |  | #REF! | 6
Supporting number at nation side | As a nation representative, I want to keep track of the number of supporting citizens in the context of a certain referendum idea, so that I can decide if declare or not the referendum, on the base of a certain threshold | 2 Med | 2 Med | 2 Med | XSM | After logging out the user should only be able to see the referendum and several info.
Supporting number at citizen side | As a citizen, I want to see the number of supporting citizens in the context of a certain referendum idea, so that I can be informed about the evolution of the referendum idea support | 2 Med | 2 Med | 2 Med | XSM | The user citizen should see the number of voters for each referendum | 2 | 2 | 2 | 3 | 3 | 3 |  |  | #REF! | 8
Supported referendum acceptance notification | As a citizen, I want to receive a notification when a supported national referendum idea has reached the 1% threshold, so that I can know it has been accepted | 3 Med | 3 Med | 3 Med | XSM | The user citizen should see the number of voters for each accepted referendum | 3 | 3 | 3 | 2 | 2 | 2 |  |  | #REF! | 9
National referendum declaration | As a nation representative, I want to declare a new national referendum, constituted by one question with "Yes" or "No" answer, so that I can obtain votes from citizens of my nation | 3 Med | 3 Med | 3 Med | XSM | It should be possible to declare a new referendum (by the national representative) | 3 | 3 | 3 | 2 | 2 | 2 |  |  | #REF! | 10
European referendum idea (consensus) | As a nation representative, I want to propose an idea for an European referendum to other European nations, so that it can be proposed to all European citizens | 1 High | 1 High | 1 High | MD | The national representative should be able to write to the other nations | 1 | 1 | 1 | 4 | 4 | 4 |  |  | #REF! | 11
European referendum declaration | As a nation representative, I want to declare a new accepted European referendum, constituted by one question with "Yes" or "No" answer, so that I can obtain votes from citizens of my nation | 1 High | 1 High | 1 High | XSM | It should be possible to declare a new European referendum (by the national representative) | 1 | 1 | 1 | 4 | 4 | 4 |  |  | #REF! | 12
Referendum display | As a citizen, I want to see the list of all referendums declared by my nation, distinguished between national ones and European ones, so that I can vote | 2 Med | 2 Med | 2 Med | LG | After logging out the user should be able to see the display with all the referendum | 2 | 2 | 2 | 3 | 3 | 3 |  |  | #REF! | 13
Nation referendum notification | As a nation representative, I want to notify the citizens of my nation about a new declared referendum, so that I can inform them | 3 Med | 3 Med | 3 Med | SM | The national representative should receive the notification to obtain the new referendum, you see it doing the get on the database | 3 | 3 | 3 | 2 | 2 | 2 |  |  | #REF! | 14
Citizen referendum notification | As a citizen, I want to be notified by my nation about a new declared referendum, so that I can be up to date | 3 Med | 3 Med | 3 Med | SM | The citizen should receive the notification to obtain the new referendum, you see it doing the get on the database | 3 | 3 | 3 | 2 | 2 | 2 |  |  | #REF! | 15
Citizen referendum vote | As a citizen, I want to vote in a referendum declared by my nation, so that I can express my opinion | 1 High | 1 High | 1 High | MD | The citizen should be able to vote in a referendum | 1 | 1 | 1 | 4 | 4 | 4 |  |  | #REF! | 16
Referendum results at nation side | As a nation representative, I want to see the results of a declared referendum, so that I can take relative measures | 1 High | 1 High | 2 Med | XSM | The citizen should be able to see the results of the referendum | 1 | 1 | 2 | 4 | 4 | 3 |  |  | #REF! | 17
Referendum results at citizen site | As a citizen, I want to see the results of a referendum declared by my nation, so that I can know the outcome | 1 High | 1 High | 1 High | LG | The national representative should be able to see the results of the referendum | 1 | 1 | 1 | 4 | 4 | 4 |  |  | #REF! | 18
European referendum ideas display (consensus) | As a nation representative, I want to see all current European referendum ideas, so that I can know other nations opinions | 3 Med | 3 Med | 3 Med | MD | In the supervisor panel, between the classical statistics you must see also a map with requests' location as markers. | 3 | 3 | 3 | 2 | 2 | 2 |  |  | #REF! | 19
European referendum idea support (consensus) | As a nation representative, I want to support or reject an idea of European referendum, so that the idea can be effectively proposed or not to European citizens | 1 High | 1 High | 1 High | XSM | the national representative should be able to see the display with all the idea for the European referendum, so vote for the first consensus | 1 | 1 | 1 | 4 | 4 | 4 |  |  | #REF! | 20
European referendum idea result (consensus) | As a nation representative, I want to see the final result of the supporting process related to an European referendum idea, so that I can know it has been accepted | 1 High | 1 High | 1 High | XSM | the national representative should be able to see the display with all the idea result for the European referendum, so allowing citizen to vote for the second consensus | 1 | 1 | 1 | 4 | 4 | 4 |  |  | #REF! | 21
European referendum result | As a nation representative, I want to see the final result of the voting process related to an European referendum, so that I can apply it if it has been approved by European citizens | 2 Med | 2 Med | 3 Med | XSM | The national representative should be able to see the results of the consensus referendum (first and second) | 2 | 2 | 3 | 3 | 3 | 2 |  |  | #REF! | 22